## Sheet1
Date | Task | Member | Initials Once Completed
3/23-3/26 | Reach out to siblings | everyone
| Reach out to parents | everyone
| Tell frats to tell their date to buy a cooler | Katie, Tyler, Melissa, Jessey, Charlotte
| Make example VT Nourish cooler | Katie
| Target NINO | Katie
| Facebook everyday reminders | shannon
| Make FB statuses | Everyone
| Share posts | everyone
| Tweet/follow twitter (@nourishvt) | everyone
| Push Sororities to buy, announce at dinners | Katie, Melissa, Shannon, Emily
2014-03-24 | Contact community service chairs | Meghan
| Pay for wholesale coolers | Melissa, Charlotte, James, Becca
2014-03-26 | Make spreadsheet for priming/sanding schedule | Charlotte
| launch marketing (contact us to sand and prime!) | Alle
| Tell customers about 3 day turnaround | Everyone, Charlotte
| Launch priming and sanding services | Melissa, Katie, Tyler, Jessey, Charlotte, Alex
2014-03-28 | Reserve Cardinal room | Jessey
| Service frat receipt form (with tax ID) | Meghan
2014-03-29 | Ask sorority women for collection help (flyer) | Alle
| Make a flyer for ^ | Alle
3/29-3/30 | Put flyer in cooler (content= collection, thank you, banding together, cooler of the week) | Alle, Jessey
| In charge of service frat volunteers | Tyler
| Stamp bands | everyone
3/31-4/2 | Bring tables and chairs | Meghan, Katie, Tyler
| Make cooler survey for testimonials | Meghan
2014-04-01 | Make star chart | katie
| Organize food for celebration | Jessey
2014-04-02 | Celebrate success | Jessey
2014-04-03 | Send cooler survey | meghan
2014-04-05 | Set up and train tweet deck | Alle
4/2-4/7 | Make marketing plan for cooler connection | Shannon, Alle, Meghan
4/5-4/10 | Write tweets (1 post a week about coolers) | Alle
2014-04-07 | Marketing plan starts for collecting coolers | shannon, alle
| Analyze survey results | Melissa, Meghan
| Meeting at 10:30 | Melissa, Meghan
2014-04-09 | Make workplan for collecting coolers | Meghan
2014-04-15 | Schedule tweets for tweet deck | Alle
| Pay Vandy for coolers/get paid | Becca, Melissa, Charlotte
4/26-4/27 | Begin collecting coolers | Everyone
mid april | Call/meet with Y-toss (bring info about project, nourish, tax ID, benefits, impacts) | Meghan