## Venture Name Work Plan
Thirft Sale WORK PLAN |  | DATE: | TIME: | LOCATION:
|  | Saturday April 2 | 11am - 3pm | Main Quad
Category | Specific Task/Item | Date to Start | Date to Finish | Person Assigned | Completed (Y/N) | Notes/Reflections
Preparation | Book Dates/Location | 2015-01-11 | 2015-01-15
| Contact Student Affairs Office | 2015-01-11 |  | Thrift Sale Venture Chair
| Meet with Advisor and sign paperwork | 2015-01-12 |  | Thrift Sale Venture Chair
| Request tables and chairs | 2015-01-13 |  | Thrift Sale Venture Chair
| Start Sponsorship Outreach | 2015-01-25 | 2015-03-04 | Venture Director
| Prepare Sponsorship Packet | 2015-01-25 | 2015-01-29 | Thrift Sale Venture Chair
| Make list of target businesses/campus offices | 2015-01-25 | 2015-01-29 | Venture Committee |  | Restaurants, clothing shops, GoGreen Campus Sustainability
| Get volunteers in pairs, train on sponsorship | 2015-01-25 | 2015-01-29 | Venture Committee
| All sponshorship requests hand delivered | 2015-02-01 | 2015-02-08 | Venture Committee
| Follow up on requests not responded to | 2015-02-12 | 2015-02-22 | Thrift Sale Venture Chair
| Collect Clothes | 2015-01-25 | 2015-03-25 | All Members
| Get boxes | 2015-01-28 |  | Thrift Sale Venture Chair |  | Decide whether to buy reusable bins, or gather cardboard from stores
| Make signs to describe collection | 2015-01-28 |  | Venture Committee |  | Include date/time of sale and contact information
| Brainstorm collection stations | Jan-26 Tuesday Weekly Meeting |  | All members, led by Venture Director |  | Campus lost and found, Sororities, Churches, Hillel, Dorm Laundry rooms and common rooms, Theater Dept. Athletic Dept
| Deliver boxes to collection stations | 2015-01-29 |  | Venture Committee
| Brainstorm other places to collect clothes | Jan-26 Tuesday Weekly Meeting |  | All members, led by Venture Director |  | Members' closets, parents' house, friends, shop at thrift stores, dollar stores, costume sale in early nov.
| Train all members on clothes collection | Jan-26 Tuesday Weekly Meeting |  | Thrift Sale Venture Chair
| Set personal goals for # of items collected | Jan-26 Tuesday Weekly Meeting |  | All members, led by Venture Director
| Make marketing plan for clothes collection | Ventures/Marketing Committee Meeting |  | Committee, led by Marketing Director
| Check in on collection stations | Mondays, weekly until March 20 |  | Venture Committee |  | Empty if full, replace signs if gone
| Find temporary storage for items | Jan-26 Tuesday Weekly Meeting |  | Thrift Sale Venture Chair |  | could split up between members or use a garage/storage space
| Organize Items |  |  |  |  | Make Mar-29 meeting fun, music, food get everyone helping out
| Pick up all final items from collection stations | 2015-03-20 | 2015-03-25 | Venture Committee |  | Add to existing storage of items
| Make signs, posters, flyers, A-frames etc | Mar-29 Tuesday Weekly Meeting |  | All members, led by Venture Director |  | 2-3 posters Advertising the Sale, 1 poster for each table, 1-2 Awareness posters – explain Nourish and give an example of what each item could buy: $1 = x amount of seeds for a Guatemalan farmer, $3 = educational material for one Guatemalan woman, 1-2 clearly explaining the pricing system
| Sort and price all items | Mar-29 Tuesday Weekly Meeting |  | All members, led by Venture Director |  | Group general items into categories, for example $1, $3, $5, and $10 Pin the price/nourish logo card on each item Organize less fancy stuff into boxes/bins and hang nice items Fold and display other clothes on tables organized by price
| Create Volunteer Schedule | Mar-22 Tuesday Weekly Meeting |  | All members, led by Venture Director
| Divide up night before and day of tasks into shifts | 2015-03-21 |  | Thrift Sale Venture Chair
| Create sign up sheet and bring to meeting | 2015-03-21 |  | Thrift Sale Venture Chair
| Get all members to sign up for shifts | Mar-22 Tuesday Weekly Meeting |  | Thrift Sale Venture Chair
| Finalize schedule | Mar-29 Tuesday Weekly Meeting |  | Thrift Sale Venture Chair
| Send all volunteers specific information | 2015-03-30 |  | Thrift Sale Venture Chair
| Text reminders to volunteers day before | 2015-04-01 |  | Thrift Sale Venture Chair
Items Needed for Venture | 1-2 Tables | 2015-03-31 |  | Thrift Sale Venture Chair
| Table Cloths | 2015-03-31 |  | Thrift Sale Venture Chair
| Hanging racks and hangers | 2015-03-31 |  | Thrift Sale Venture Chair
| Nourish banner | 2015-03-31 |  | Thrift Sale Venture Chair
| Flyers and posters with information about Nourish and about prices | 2015-03-31 |  | Thrift Sale Venture Chair
| Tape | 2015-03-31 |  | Thrift Sale Venture Chair
| Markers | 2015-03-31 |  | Thrift Sale Venture Chair
| Balloons/Streamers – to attract customers | 2015-03-31 |  | Thrift Sale Venture Chair
| Speakers/music – if campus allows it | 2015-03-31 |  | Thrift Sale Venture Chair
| Extra small cards and safety pins for pricing | 2015-03-31 |  | Thrift Sale Venture Chair |  | small card with the nourish logo, mission and item’s price
| Receipts – a quarter sheet flyer with meeting info and thank you from Nourish | 2015-03-31 |  | Thrift Sale Venture Chair
| Email sign up sheet | 2015-03-31 |  | Thrift Sale Venture Chair
| Cash box with change (about $100 of $1s and $5s) | 2015-03-31 |  | Thrift Sale Venture Chair
| Square for credit cards, | 2015-03-31 |  | Thrift Sale Venture Chair
Marketing | Marketing committee lead brainstorm for additional ideas | Feb-2 weekly meeting |  | Marketing committee
| Research ad prices | 2015-02-26 | 2015-03-01 | Marketing committee |  | In school paper and local papers
| Decide on ad purchase, and take next step | 2015-03-05 |  | Marketing Director and Venture Director |  | Next steps: get ad designed, send in by deadline
| Make announcements in other student group meetings | 2015-03-05 | 2015-03-25 | Marketing committee |  | Make calendar of meetings, contact presidents, volunteers sign up to announce
| Post in all campus event calendars | 2015-02-10 |  | Venture Committee
| Create plan for Social Media campaign, implement weekly plan | 2015-02-10 | 2015-04-02 | Marketing committee |  | Create Facebook event, change profile pictures, and post on Nourish Twitter and Instagram. Take photos of members modeling some of the best items and post on social media
| Flyers/Posters: designed, printed, distributed | 2015-02-10 | 2015-03-20 | Marketing committee
Day of marketing to drive customers to the sale
| Music | 2015-04-02
| A-frames | 2015-04-02 |  |  |  | Make at prep-party
| Posters/Flyers | 2015-04-02
| Balloons/Streamers | 2015-04-02
| Volunteers in their Nourish shirts standing in high traffic areas to encourage people to go | 2015-04-02 |  |  |  | Include this role in volunteer schedule
| All members and volunteers text friends to come and help create a crowd | 2015-04-02 |  |  |  | Tell all members at meeting
To Do the Day Before | Clothes and supplies ready to bring the next morning | 2015-04-01 |  | Thrift Sale Venture Chair
| Reminder email/text to all volunteers about schedule and items they are bringing | 2015-04-01 |  | Thrift Sale Venture Chair
To Do the Day Of | Start setting up 1-2 hours before the sale starts
| Move clothes and supplies into cars |  |  | Volunteers
| Set-up Tables and Racks |  |  | Volunteers
| Get tables and chairs delivered (by volunteers or by campus) |  |  | Volunteers
| Set up all clothes |  |  | Volunteers
| Place additional/excess clothes in labeled garbage bags below corresponding tables for easy restocking as supply diminishes |  |  | Volunteers
| Set up day off marketing (balloons, posters, A-Frame, music) |  |  | Volunteers
| Train all volunteers |  |  | Volunteers
| Point person to deal with questions or problems as they come up |  |  | Thrift Sale Venture Chair
| During Sale |  |  | Volunteers
| Remind volunteers about sales tactics |  |  | Thrift Sale Venture Chair
| Hand out “receipt” to each customer |  |  | Volunteers
| Have awareness table well-stocked with information |  |  | Volunteers
| Volunteers in high traffic areas to flyer and direct people to the sale |  |  | Thrift Sale Venture Chair
| Maintain the tables in good condition by folding and restocking often |  |  | Volunteers
| Price and display any day-of clothing donations |  |  | Volunteers
| Last 30 minutes: make everything $1 (and advertise it as such!) |  |  | Thrift Sale Venture Chair |  | Don't want to have leftover clothes
To Do Post-Venture | Clean-Up | 2015-04-02 |  | Volunteers
| Deliver tables/chairs back | 2015-04-02 |  | Volunteers
| Drive all leftover clothes to a near by thrift store, or decide where to store them for next year’s sale | 2015-04-02 |  | Volunteers
| Submit all receipts to finance director to be submitted for reimbursement to either school funding board or Nourish National office depending on funding source. | Monday Apr 4 |  | Thrift Sale Venture Chair
| Hand-written thank you notes to all advisers, donors, and sponsors | Monday Apr 4 |  | Venture Committee
| Follow-up Chapter Meeting and Write up on lessons learned and how to improve for next year | Apr 5 Tuesday Weekly Meeting |  | All members, led by Venture Director
Past Lessons Learned (from other Chapters)
Logistics
Reserve the application longer then you plan to sell, give time for set up and then you can stay open longer if needed
Plan the whole process from a customer’s perspective, how do they arrive, how do they explore, how do they check out
Bring a mirror and create a space for people to try things on
Invest in a hanging rack (cheap on amazon) or see if you can borrow from somewhere on campus, hanging keeps items visual and looking nice
Price items with a neon circle
Have a email sign up list at check out for people to learn more about Nourish and attend the next meeting
Get Nourish team T-Shirts for easy visibility at sale
Finances
Bring change in a cash box, bring the square (but have a minimum credit card purchase)
Don’t be afraid to price things above $5
You could offer 2 $2 items for $5 to increase sales
Products
Cheap costumes sell really well, consider going to other thrift stores or dollar stores to purchase things to supplement what is donated
It’s great to offer a free item with a certain amount purchase. UCLA gets donated tote bags and gives them away free with a $20 purchase
Quality is key – price high quality items higher
Do clothing drive earlier or do two drives (if storage isn’t an issue) so more quality items can be collected